## Checklist
Sr. No. | Department | Checklist / Action | Owner | Status | Remarks
1 | Commercial | Confirm Flat 50% offer applicability on 5th evening by 5pm | Rajendra/Amrit | Pending
2 | Commercial | Confirm T&C | Rajendra/Amrit | done
3 | BnM | Confirm exclusions | Joshika | done
4 | IT/POS | Confirm offer configuration in POS | Naren/IT | Pend
5 | Queue Management | Define customer queue area | Store Manager/SLP | in Progress
6 |  | Arrange queue managers | Store Manager/SLP | done
7 |  | Create entry and exit routes | Store Manager/SLP | Working
8 |  | Install queue signage | Store Manager/SLP | Working
9 |  | Allocate queue-management staff | Store Manager/SLP | Working
10 | SLP | Arrange additional security manpower | Ravinder Kaur/ALPO | done
11 |  | Deploy entrance/exit security | Ravinder Kaur/ALPO | done
12 |  | Deploy billing-area security if required | Ravinder Kaur/ALPO | NA
13 |  | Review CCTV coverage | Ravinder Kaur/ALPO | done
14 |  | Identify CCTV blind spots | Ravinder Kaur/ALPO | checked
15 |  | Brief team on shoplifting prevention | Ravinder Kaur/ALPO | will brief 5th
16 |  | Brief team on crowd-control procedure | Ravinder Kaur/ALPO | will brief 5th
17 | Housekeeping | Arrange additional housekeeping manpower | FM | Done
18 |  | Arrange additional cleaning supplies | FM | Done
19 | Staffing | Forecast additional manpower requirement | Store Manager | Send temp staff requirement for 6th sep
20 |  | Finalize sales-floor manpower | Store Manager | done
21 |  | Finalize cashier manpower | Store Manager | done
22 |  | Finalize stockroom manpower | Store Manager | done
23 |  | Arrange floating/reliever staff | Store Manager | done
24 |  | Prepare absenteeism backup plan | Store Manager | done
25 |  | Communicate shift roster | Store Manager | done
26 |  | Deploy additional peak-hour staff | Store Manager | Working
27 | Employee Welfare | Prepare staggered break roster | Store Manager | done
28 |  | Arrange drinking water | Store Manager | done
29 |  | Arrange tea/coffee/refreshments | Store Manager | done
30 |  | Arrange meals for extended shifts | Store Manager | done
31 |  | Ensure break area availability | Store Manager | done
32 | Stock | Identify Ageing/deval/liquidation SKUs by 4th Sep | Store Manager | Working
33 |  | Send additional stock requirement/ plan ISTs | Store Manager/Joshika | Working
34 |  | Complete stockroom to be vacate by 4th Sep | Store Manager | Working
35 |  | Monitor stockouts hourly | Store Manager | Working
36 | Consumables | Order additional shopping bags | Joshika | To be dry clean on immediate basis
37 |  | Order additional carry bags | Joshika | Arrange brown bags locally in case of sortage
38 |  | Arrange POS rolls | Rajendra/Amrit | arrange locally
39 |  | Arrange stationery | Store Manager | done
40 | VM | Complete VM reset | Avanish | Working
41 |  | Install 50% OFF entrance communication | Avanish | pending
42 |  | Install window communication | Avanish | Pending
43 |  | Create promotional focal points | Avanish | done
44 |  | Move ageing/high value products to high-traffic areas | Store manager | Working
45 |  | Reset unnecessary fixtures | Avanish | NA
46 |  | Arrange Easel/Acrylics/Barkers/tentcards | Avanish | Working
47 |  | Signage for No gift wrapping | Avanish | Pending
48 |  | Signage for No Credit Note | Avanish | Pending
49 |  | Signage for No Exchange No returns | Avanish | Pending
50 |  | Creative for Danglers to be hanged at store entrance | Avanish | Pending
51 |  | Ensure aisles have adequate clearance | Avanish | Pending
52 | POS | Arrange additional MPOS | Store Manager | 1 is Avilable
53 |  | Test all POS terminals on 4th evening | Store Manager | Pending
54 |  | Test 50% discount on 4th evening | Store Manager | Pending
55 |  | Test EDC terminals | Store Manager | done
56 |  | Test UPI/payment methods | Store Manager | done
57 |  | Check printer functionality | Store Manager | done
58 |  | Check internet connectivity | Store Manager | done
59 |  | Allocate cashier to each POS | Store Manager | done
60 |  | Arrange sufficient cash float | Store Manager | done
61 |  | Arrange additional change/denominations | Store Manager | done
62 |  | Define cash collection frequency | Store Manager | done
63 |  | Arrange additional manual bill books | Store Manager | done
64 |  | Prepare/Refresh manual billing procedure | Rajendra/Amrit | Working
65 |  | Define manual discount authorization | Rajendra/Amrit | Pending
66 |  | Keep extra stationery- Calculators/carbon papers/pens/staplers etc | Store Manager | done
67 |  | Arrange stamp for No Exchnage No returns | Store Manager | done
68 |  | No Gift wrapping to be allowed | Store Manager | done
69 |  | No CN to be entertained | Store Manager | done
70 |  | No DVs/Luxe card to be entertained | Store Manager | done
71 |  | Define POS-reconciliation process | Rajendra/Amrit | Working
72 | Marketing | Finalize campaign artwork | Bala | done
73 |  | Finalize campaign T&Cs | Bala | done
74 |  | Update social media communication | Bala | done
75 |  | Update Print ad communication | Bala | done
76 |  | Update radio ad communication | Bala | Working
77 |  | Update NPI/influencer/SMS blast/RCS/other communcation | Bala
78 |  | Update Standalone stores marketing plan | Bala
79 |  | Communication to entire Ril data base through e-mail/People first/mhere/SMS | Bala
80 |  | Coordinate mall marketing for screens/hoarding/standees etc | Bala
81 |  | Share campaign id for potential buyers (>10K) shopped in last 6 months | Bala
82 |  | Install in-store marketing communication | VM Team/Store manager
83 |  | Creative for NPI for Tier2/3 stores | Bala
84 |  | Communication in RBL brands within same mall | Store manager | done
85 | Customer Service Desk | Prepare sale FAQs | Training team
86 |  | Define complaint escalation process | Store Manager | Pending
87 |  | Arrange water bottles | Store Manager | done
88 |  | Keep First Aid box | Store Manager | done
89 |  | Keep department wise escalation matrix | Store Manager | done
90 |  | Assign customer-service employee | Store Manager | done
91 | Safety & Security | Check emergency exits | SLP/Store Manager | done
92 |  | Check fire extinguishers | SLP/Store Manager | done
93 |  | Check emergency lighting | SLP/Store Manager | done
94 |  | Brief employees on evacuation | SLP/Store Manager | done
95 |  | Brief team on lost-child procedure | SLP/Store Manager | done
96 |  | Availability of First aid kit | SLP/Store Manager | done
97 |  | Define lost-child escalation | SLP/Store Manager | done
98 | Store readiness on 5th Evening | Open store at 7am on 6th Sep | Store Manager | NA
99 |  | Complete final store walk | Store Manager | Pending
100 |  | Check duty roaster | Store Manager | Pending
101 |  | Confirm security deployment | Store Manager | Pending
102 |  | Confirm POS readiness | Store Manager | Pending
103 |  | Confirm stock replenishment | Store Manager | Pending
104 |  | Confirm VM/signage | Store Manager | Pending
105 |  | Confirm queue setup | Store Manager | Pending
106 |  | Conduct final staff briefing | Store Manager | Pending
107 | Closing | Complete pending billing | Store Manager | Pending (Brifed)
108 |  | Reconcile each POS | Store Manager | Pending (Brifed)
109 |  | Reconcile cash/card/UPI | Store Manager | Pending (Brifed)
110 |  | update all manual bills | Store Manager | Pending (Brifed)
111 | Mall coordination | Permission for additional security guards | Store Manager | Done
112 |  | Permission for early store opening- 7am | Store Manager | NA
113 |  | Permission to allow customers in mall- 9am | Store Manager | NA
114 |  | Arrange additional Q managers by 4th Sep | Store Manager | done
115 |  | Inform mall team on Doctor/Ambulance availbility | Store Manager | Informed
116 | Support functions | Roaster for Tail office/regional office employees to be shared by 1st Sep | HR head | done
117 |  | 48 hrs (5-6th Sep) extended support required from all support functions (IT/comm/FM/others) | Ops head/BH | Pending
118 | Attractions | No Birthday Parties on 6th sep | Store Manager | done
119 | SCM | No deliveries to be planned on 5th & 6th Sep from DC/DSD | Ajay Singh/Joshika | pending
120 | Ecom | No ecom order to be processed on 6th Sep | Kanisht/Store manager | done
121 | Training | No MA on Blowout week, Agency to be informed | Chetan Shetty | done
122 | Preorders | Connect with at-least 5 local vendors for preorders | Store Manager | Connect with 2 rest will meet.

## Emergency Escalation matrix
Emergency / Escalation Matrix | SPOC Name | Contact No.
POS failure | Naren das | 7977708420
Internet failure | Lal chand | 9354380324
Payment failure | Rajendra/Amrit | 8600142713 / 9321825687
Offer Issues | Pooja/Fudail | 9769575917 / 9099626543
Customer dispute | Store Manager
Suspected theft | ALPO/LPA
Medical emergency | Mall Emergency Team
Fire | Mall Security
Lost child | Mall Security
Power failure | Mall team/FM
Water leakage | Mall team/FM